## Source of Project Cost
Source of Project Cost
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK
PROJECT DESIGN | Develop Functional Specifications | 10 | 50 | 40 | 10 | 0 | 550
| Develop System Architecture | 8 | 50 | 30 | 5 | 0 | 435
| Develop Preliminary Design Specification | 12 | 50 | 50 | 15 | 0 | 665
| Develop Detailed Design Specifications | 15 | 50 | 60 | 20 | 0 | 830
| Develop Acceptance Test Plan | 10 | 50 | 20 | 10 | 0 | 530
| Subtotal | 55 |  | 200 | 60 | 0 | 3010
PROJECT DEVELOPMENT | Develop Components | 0 | 0 | 0 | 0 | 0 | 0
| Procure Software | 0 | 0 | 500 | 0 | 0 | 500
| Procure Hardware | 0 | 0 | 300 | 0 | 0 | 300
| Development Acceptance Test Package | 0 | 0 | 0 | 0 | 0 | 0
| Perform Unit/Integration Test | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 |  | 800 | 0 | 0 | 800
PROJECT DELIVERY | Install System | 20 | 50 | 200 | 100 | 0 | 1300
| Train Customers | 25 | 50 | 250 | 150 | 0 | 1650
| Perform Acceptance Test | 15 | 50 | 150 | 50 | 0 | 950
| Perform Post Project Review | 12 | 50 | 100 | 20 | 0 | 720
| Provide Warranty Support | 0 | 0 |  | 0 | 0 | 0
| Archive Materials | 0 | 0 | 50 | 0 | 0 | 50
| Subtotal | 72 |  | 750 | 320 | 0 | 4670
PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 10 | 50 | 40 | 20 | 0 | 560
| Internal Status Meetings/Reports | 8 | 50 | 30 | 10 | 0 | 440
| Third-Party Vendor Interface | 6 | 50 | 50 | 10 | 0 | 360
| Interface to Other Internal Departments |  | 0 | 0 | 0 | 0 | 0
| Configuration Management | 10 | 50 | 40 | 20 | 0 | 560
| Quality Assurance | 15 | 50 | 60 | 30 | 0 | 840
| Overall Project Management | 20 | 50 | 80 | 50 | 0 | 1130
| Subtotal | 69 |  | 300 | 140 | 0 | 3890
OTHER COST | Other cost | 0 | 0 | 0 | 0 | 180 | 180
| Other cost | 0 | 0 | 0 | 0 | 0 | 0
| Other cost | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 |  | 0 | 0 | 180 | 180
Subtotals |  | 196 |  | 2050 | 520 | 180 | 12550
Risk (Contingency) |  | 0 | 0 | 0 | 0 | 0 | 0
Total (Scheduled) |  | 196 |  | 2050 | 520 | 180 | 12550

## Expenditures Over Time
Expenditures Over Time
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| INSTALLATION | Install System | 1300 | 2025-01-05 | Labor, material, and travel for installation
|  | Train Customers | 1650 | 2025-01-06 | Employee training costs and materials
|  | Perform Acceptance Test | 950 | 2025-01-07 | Testing labor and resources
|  | Perform Post Project Review | 720 | 2025-01-08 | Labor and documentation
|  | Provide Warranty Support | 0 | N/A | N/A
|  | Archive Materials | 150 | 2025-01-09 | Document archival costs
|  | Subtotal | 4770
| PLANNING (RFP) | Develop Functional Specifications | 550 | 2024-12-01 | Labor and material for creating specifications
|  | Develop System Architecture | 485 | 2024-12-02 | Labor and material for architectural planning
|  | Develop Preliminary Design Specifications | 665 | 2024-12-03 | Drafting and material preparation
|  | Develop Detailed Design Specifications | 830 | 2024-12-04 | Detailed labor and resources
|  | Develop Acceptance Test Plan | 530 | 2024-12-05 | Planning acceptance criteria
|  | Achieve Materials | 0 | N/A | N/A
|  | Subtotal | 3060
| PLANNING 2 | Customer Progress Meetings | 560 | 2024-12-06 | Labor and resources for client updates
|  | Internal Status Meetings | 560 | 2024-12-07 | Internal reporting and progress tracking
|  | Third-Party Vendor Interface | 330 | 2024-12-08 | Coordination with external vendors
|  | Configuration Management | 560 | 2024-12-09 | Configuration and planning resources
|  | Provide Warranty Support | 0 | N/A | N/A
|  | Achieve Materials | 0 | N/A | N/A
|  | Subtotal | 2010
| CONSTRUCTION | Procure Software | 500 | 2024-12-10 | Acquisition of required software licenses
|  | Procure Hardware | 350 | 2024-12-11 | Acquisition of hardware components
|  | Develop Components | 0 | N/A | N/A
|  | Develop Acceptance Test Package | 0 | N/A | N/A
|  | Provide Warranty Support | 0 | N/A | N/A
|  | Achieve Materials | 0 | N/A | N/A
|  | Subtotal | 850
| TEST & DELIVERY | Perform Unit/Integration Test | 860 | 2024-12-12 | Labor and testing resources
|  | Quality Assurance | 990 | 2024-12-13 | Testing and quality verification
|  | Perform Acceptance Test | 0 | N/A | N/A
|  | Perform Post Project Review | 0 | N/A | N/A
|  | Provide Warranty Support | 0 | N/A | N/A
|  | Achieve Materials | 0 | N/A | N/A
|  | Subtotal | 1850
| PROJECT TOTAL |  |  | 12550 | 12550

## Cumulative Project Costs
Projected vs. Actual Costs
MONTHLY COST
CUMULATIVE COST

## Data Worksheet
Project Data Worksheet
| MONTH | PROJECTED MONTHLY COST | ACTUAL MONTHLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 3940 | 3710 | 3940 | 3710
| 2 | 3050 | 3140 | 6990 | 6850
| 3 | 3580 | 3700 | 10570 | 12550