{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["WBS"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"WBS","index":0,"n_rows":32,"n_cols":11,"rows_kept":32,"cut":false,"hidden":false,"merged":[[0,0,0,16383]]}
[]
["WBS Number","Task Name","WBS Description","Must Start by Date","Must End by Date","Task Level of Effort\n(in hours)","Task Duration\n(in days)","Predecessor\n(Finish-to-Start Dependency)\n(comma separated)","Resource Name(s)","Author\n(of Item for follow-on questions)","Status (% Complete)"]
["1","Define Project Scope ","Outline the purpose, scope, and deliverables of the \"How to Process an Order\" project.","2024-11-26","2024-11-26",4,0.5,null,"Michael Sullivan","Prof. Andrew Mooney",100]
["1.1","Identify Project Objectives","Clearly define the goals of the project.","2024-11-27","2024-11-28",2,0.25,1,"Michael Sullivan","Prof. Andrew Mooney",100]
["1.2","Outline Deliverables","Specify what forms, documents, and workflows will be created.","2024-11-29","2024-11-30",2,0.25,1.1000000000000001,"Michael Sullivan","Prof. Andrew Mooney",100]
["1.3","Define Success Criteria","Establish how the success of the project will be measured.","2024-12-01","2024-12-01",2,0.25,1.2,"Michael Sullivan","Prof. Andrew Mooney",100]
["2","Create Order Inquiry Form","Design a form to capture initial customer inquiries for photography services.","2024-12-02","2024-12-03",4,0.5,1.3,"Michael Sullivan","Prof. Andrew Mooney",100]
["2.1","Research Existing Templates","Analyze industry standards for order forms.","2024-12-04","2024-12-05",2,0.25,2,"Michael Sullivan","Prof. Andrew Mooney",100]
["2.2","Draft Inquiry Form","Create a draft of the order inquiry form for customer use.","2024-12-06","2024-12-07",2,0.25,2.1,"Michael Sullivan","Prof. Andrew Mooney",100]
["2.3","Review and Finalize Form","Review the form and finalize it.","2024-12-08","2024-12-08",2,"0,25",2.2000000000000002,"Michael Sullivan","Prof. Andrew Mooney",100]
["3","Develop Customer Details Form","Create a form to collect customer information name, contact, preferences, ect.","2024-12-09","2024-12-10",3,0.375,2.2999999999999998,"Michael Sullivan","Prof. Andrew Mooney",100]
["3.1","Identify Required Information","Determine the customer details needed for order processing.","2024-12-11","2024-12-12",2,0.25,3,"Michael Sullivan","Prof. Andrew Mooney",100]
["3.2","Draft Customer Details Form","Create a draft of the customer details form.","2024-12-13","2024-12-13",2,0.25,3.1,"Michael Sullivan","Prof. Andrew Mooney",100]
["4","Design Scheduling Checklist","Develop a checklist for scheduling customer photo sessions, including time slots and location details.","2024-12-14","2024-12-15",3,0.375,3.2,"Michael Sullivan","Prof. Andrew Mooney",100]
["4.1","Identify Key Scheduling Steps","Break down the scheduling process into individual steps.","2024-12-16","2024-12-17",2,0.25,4,"Michael Sullivan","Prof. Andrew Mooney",100]
["4.2","Draft Scheduling Checklist","Create a checklist to guide staff in scheduling customer sessions.","2024-12-18","2024-12-19",2,0.25,4.0999999999999996,"Michael Sullivan","Prof. Andrew Mooney",100]
["4.3","Validate Checklist","Validate the checklist to ensure all scheduling needs are covered.","2024-12-20","2024-12-20",2,"0,25",4.2,"Michael Sullivan","Prof. Andrew Mooney",100]
["5","Create Workflow Diagram","Map out the entire order process from inquiry to photo delivery.","2024-12-21","2024-12-22",4,0.5,4.3,"Michael Sullivan","Prof. Andrew Mooney",100]
["5.1","Identify Workflow Steps","Break down the full process into clear, sequential steps.","2024-12-23","2024-12-24",2,0.25,5,"Michael Sullivan","Prof. Andrew Mooney",100]
["5.2","Draft Process Flow Diagram","Create a draft diagram using a tool to illustrate process","2024-12-25","2024-12-25",2,0.25,5.0999999999999996,"Michael Sullivan","Prof. Andrew Mooney",100]
["5.3","Review and Revise Diagram","Review the diagram and revise as needed.","2024-12-26","2024-12-27",2,0.25,5.2,"Michael Sullivan","Prof. Andrew Mooney",100]
["6","Write SOP Document","Document all processes, steps, roles, and responsibilities in a Standard Operating Procedure.","2024-12-28","2024-12-29",4,".0.5",5.3,"Michael Sullivan","Prof. Andrew Mooney",100]
["6.1","Create SOP Outline","Develop a structured outline for the SOP.","2024-12-29","2024-12-30",2,0.25,6,"Michael Sullivan","Prof. Andrew Mooney",100]
["6.2","Write Detailed Instructions","Document detailed steps for each task in the process.","2024-12-30","2024-12-31",2,0.25,6.1,"Michael Sullivan","Prof. Andrew Mooney",100]
["6.3","Review and Finalize SOP","Review the SOP and finalize it.","2025-01-01","2025-01-01",2,0.25,6.2,"Michael Sullivan","Prof. Andrew Mooney",100]
["7","Develop Training Materials","Create presentations and guides for staff training.","2025-01-02","2025-01-03",3,0.375,6.3,"Michael Sullivan","Prof. Andrew Mooney",100]
["7.1","Schedule Training Sessions","Organize and schedule sessions with all employees.","2025-01-04","2025-01-05",2,0.25,7,"Michael Sullivan","Prof. Andrew Mooney",100]
["7.2","Conduct Training","Deliver training to staff and answer questions.","2025-01-06","2025-01-07",2,0.25,7.1,"Michael Sullivan","Prof. Andrew Mooney",100]
["8","Follow-Up and Review Form","Collect feedback from staff and refine SOP based on implementation experience.","2025-01-08","2025-01-10",3,0.375,7.2,"Michael Sullivan","Prof. Andrew Mooney",100]
["8.1","Gather Staff Feedback","Collect feedback on the usability and effectiveness of the SOP.","2025-01-11","2025-01-14",2,0.25,8,"Michael Sullivan","Prof. Andrew Mooney",100]
["8.2","Analyze Feedback","Identify areas for improvement based on staff feedback.","2025-01-15","2025-01-17",2,0.25,8.1,"Michael Sullivan","Prof. Andrew Mooney",100]
["8.3","Revise SOP and Processes","Make updates to the SOP and processes to address feedback.","2025-01-18","2025-01-20",2,0.25,8.1999999999999993,"Michael Sullivan","Prof. Andrew Mooney",100]